## Sheet1
Giao diện | Launch Activity | Huy | Week1
| Main Activity (Menu Screen) | Hà | Week1
| Stories Activity (ListView) | Sỹ | Week1
| Stories Activity (Fake Data + Custom) | Quang | Week1
| Drawable Layout | Hà | Week3
| Detail Activity | Sỹ | Week3
| Edit, Design Layout, Color, Background | Quang | Week3
| Navigation Drawer | Hà | Week5
| Stories Activity (Bổ sung SearchView) | Huy | Week5
| Chỉnh lại bố cục + Info Activity | Sỹ | Week5 + 7
| Chỉnh sửa giao diện | Quang | Week5
Java Code | Launch Activity (Intent) | Huy | Week2
| Story class | Hà | Week2
| Main Activity (Intent các button) | Sỹ | Week2
| Intent menu item | Quang | Week2
| Chuẩn bị dữ liệu truyện + audio | Huy,Hà | Week4
| Đưa dữ liệu lên firebase | Quang,Sỹ | Week4
| MainActivity (Lấy dữ liệu trên firebase (JSON) | Quang | Week4
| Lấy dữ liệu từ Firebase đổ vào listview | Quang | Week6
| Intent chuyển bundle từ StoriesActivity sang DetailActivity | Quang | Week7
để hiển thị nội dung chi tiết truyện
| MediaPlayer (MP3) play,pause | Quang | Week8
| Hàm search truyện + Mục yêu thích | … | …